## Checklist_TD
Monitoring guidance table
Monitoring Mission
I. Preparatory desk review
1. CRIS Project reference no.
2. Project Title
3. Total project budget/contract value, indicating EC and cofinancing contribution
4. Contract start dates and foreseen duration, incl. addenda
5. Planned results and indicators (as of logframes)
6. Contracting Authority/ Contractor/Beneficiary/Consultant
7. Documents to be requested and received prior to the mission (contracts, reports, detailed implementation schedule)
8. List of planned meetings, sites to be visited and participants (name, institution, location, transport) + agenda attached
II. On the spot monitoring
9. Overview on the visit: (progress in line with logframe, results achieved + main activities completed, findings, recommendations, future plans, reached agreements, benchmarks respected? etc)
10. Are the project results and activities in line with the fiche, logframe (incl. indicators)?
11. Are the project purpose and objectives likely to be achieved in a sustainable manner as foreseen in the fiche at the end of the project?
12. Is the timetable /implementation plan realistic? Which delays have occurred and why?
13. Confirm that conditionalities have been met and project sequencing has been adhered to
14. Verify that the project management is adequate and the existence and operationability/usefulness of the Steering Committee to manage the project
15. Visibility requirements of the FM/fiche/contract met? Appropriate and visible use of the EU symbol, commemorative boards opening ceremony, media publicity?
16. Verify whether procurements are within the foreseen procurement plan and comment on possible delays, procedural issues or problems to be followed up
17. Confirm that the procurement procedures have been correctly applied
18. Payment flow to the beneficiary/contractor in line with plans; national, own and other cofinancing has been provided as planned?
19. In case of works: supervision, inspection and safety measures have been adequate? In case of Twinning: verify adherence to the Twinning Manual in organising activities
20. Reporting to and monitoring by the contracting authority has been adequate? Documentation properly stored/archived?
21. If any, describe recommendations, detailed follow up actions required, who they are addressed to and a timetable for their implementation
22. Flag any suspected irregular occurances?
23. List of annexes, documents, pictures or other supporting materials attached (if applicable)
| Monitoring Expert | Visa by Project Leader
| Name | Name
| Signature | Signature
| Date | Date